## Sheet1
Jurisdiction | Mitigation Action |  | Hazard(s) Addressed |  | Responsible Party/Parties to Implement |  |  |  |  | Status - Check One |  |  |  | Status Details | Relevance - Check One |  | Relevance Details
|  | Previous Priority |  | Protecting which type of assets |  | Local planning mechanism identified to implement action | Initial Target Date for Completion | Estimated Cost | Funding Source(s) | Completed | Initiated but Not Completed | Ongoing Type of Activity | Not Initiated | If not completed, identify barriers to implementation (i.e., lack of political support, funding, staff availability, etc.) or explain why the action is an ongoing one (i.e., acquisition of hazard prone land for open space can be completed for a given parcel or group of parcels, but there may be many more opportunities in the community and so the activity may be carried forward) | Still Relevant - Carry Forward to Updated Mitigation Strategy | No Longer Relevant - Omit from Updated Mitigation Strategy | If you checked the box that the project is being carried forward to the updated mitigation strategy, describe if and how it has changed from the 2009 Plan. If you checked the box that the project is being omitted from the updated mitigation strategy, provide a brief explanation.
Monmouth County | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Monmouth County | Project #1 - Storage of Critical Equipment (Retrofit existing facilities for storage of critical equipment presently housed at floodprone highway district garages - #1 in Belfort and #8 in Hazlet) | H | Flooding, Storms, Nor’easter & Storm Surge | Existing | Dept. of Public Works & Engineering & Building & Grounds | Capital Improvement Program | 2009-2010 | $1.5 million | PDMP, FMAP, County Budget
Monmouth County | Project # 2A – Regional Stormwater Management Hydrological and Drainage Studies | M | Flooding, Storm Surges | Existing | Various County & Municipal Agencies | State Permits, Property Easements & Stormwater Mgmt Plan | 2009-2010 | 500000 | PDMP, FMAP, County Budget
Monmouth County | Project # 2B – Regional Stormwater Management Acquisition/Construction of Sediment Management Site | L | Flooding, and Storm Surge | Existing | Various State, County & Municipal Agencies | State Permits & Property Acquisition | 2012-2013 | $6.5 million | PDMP, FMAP, State, County & Municipal Funds
Monmouth County | Project # 3 – Utility Protection (Protective Measures for Utility Rights of Way) | M | Flooding, Hurricanes, Nor’easter, High Wind & Fire | Existing | County OEM, Utility Companies | State permits, OEM Planning | 2010 | $2.5 Million | PMDP, FMAP, Utilities & County Budget
Monmouth County | Project # 4 – Purchase Properties (Purchase of Flood Prone Properties) | M | Floods, nor'easter & hurricanes | Existing | County Parks, other County agencies and Non profit conservation agencies | Open Spac3 Plan | 2009-2013 | $15 Million | PDMP, FMAP, State, County, Municipalities & Non-Profits
Monmouth County | Project # 5 – Roads and Bridges (Upgrade Critical County Roads and Bridges Impacted by Flooding) | M | Floods, Storm Surge, Dam Failure, Wind, Nor'easter & Hurricane | Existing | County Dept. of Public Works & Engineering, & Municipal agencies | Capital Improvement Program, State Permits, OEM Planning | 2009-2013 | $17.7 Million | PDMP, FMAP, State, County
Monmouth County | Project #6 - Shelter Hardening (Special Needs Shelter Hardening) | H | Floods, wind, winter storms, tornado, nor'easter, hurricanes & excessive heat |  | County Health Department and County OEM
Aberdeen, Township of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Aberdeen, Township of | Create a mitigation outreach program that helps residents prepare for disasters | H | All |  | Office of Emergency Management
Aberdeen, Township of | Develop specific mitigation solutions for flood prone roadways, specifically State Highway 35 at Long Neck Creek, Lakeshore Drive and Greenwood Avenue, and Amboy Avenue, under the leadership of NJDOT. Develop a work plan for when sites will be surveyed and what role can the local government play in selection and implementation of mitigation activities (i.e., any monetary or contextual support through the local capital improvement plan). | M | Flooding caused by floods, hurricanes, and nor'easters |  | Township Manager, Township Engineer, NJDOT, Monmouth County Highway Department
Allenhurst, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Allenhurst, Borough of | Action 2B Mitigation Outreach | H | All |  | OEM
Allenhurst, Borough of | Action 11A Purchase NOAA Weather Radios for critical facilities | H | All |  | Police
Allenhurst, Borough of | Action 11B Educate residents about winter driving and winter hazards | M | Winter storm related hazards |  | OEM and Police
Allentown, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Allentown, Borough of | Educate residents about what to do before, during and after a flood | 1 | Flooding |  | OEM and Deputy OEM
Allentown, Borough of | Develop an inventory of addresses that could be affected by a wildfire. Use inventory and develop a route alerting system. | 2 | Wildfires |  | OEM and Deputy OEM
Allentown, Borough of | Reconstruct an existing dam that runs below County Route 539. Dam failure cause major private and public property damage. This would also greatly affect and damage municipal sewer plant. | 3 | Dam failures |  | OEM and Deputy OEM
Asbury Park, City of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Asbury Park, City of | Repair damages, storm drains | M | Flooding |  | City Engineer
Asbury Park, City of | Replace bulkhead and dredge Sunset Lake | H | Flooding |  | City Engineer
Asbury Park, City of | Replace bulkhead and dredge Wesley Lake | H | Flooding |  | City Engineer
Atlantic Highlands, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Atlantic Highlands, Borough of | Project #1 - Hillside Road, Phase II | H (#1) | Flooding/Erosion |  | Mayor and Council
Atlantic Highlands, Borough of | Project #2 - Fireman's Field | M (#2) | Flooding |  | Mayor and Council, Atlantic Highlands Fire Department
Atlantic Highlands, Borough of | Project #3 - Bayside Drive Erosion Stabilization | M (#3) | Erosion |  | Mayor and Council
Avon-by-the-Sea, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Avon-by-the-Sea, Borough of | Continue outreach efforts to residents and businesses through the quarterly Borough newsletter and Borough web site | M | Flooding, Wind, Winter Storms |  | OEM Coordinator
Avon-by-the-Sea, Borough of | Establish a resource library at the Borough Library to include printed materials as well as electronic data from the internet related to natural disasters | M | Flooding, Wind, Winter Storms |  | Librarian, OEM Coordinator
Avon-by-the-Sea, Borough of | Evaluate vulnerabilities of existing emergency facilities including the Municipal Building (PD and FD HQ), EMS HQ, and Water Treatment Plant. Develop action plan for deficiencies identified. | H | Flooding, Wind, Winter Storms |  | OEM Coordinator, Construction Department
Avon-by-the-Sea, Borough of | Expand upon the lake management efforts for the Sylvan Lake to reduce damage from flooding. Include additional wall replacement and dredging activities to remove silt from streams feeding the lake. | L | Flooding |  | Sylvan Lake Commission (a joint agency of Avon By the Sea and Bradley Beach)
Belmar, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Belmar, Borough of | Continue to implement projects identified in the Capital Improvement Plan and seek grant funding when possible to offset project costs | M | All |  | Belmar DPW
Belmar, Borough of | Stabilization of shoreline | M | Coastal erosion |  | Belmar DPW
Belmar, Borough of | Lake Como Flooding Mitigation Project | H | Flooding |  | Belmar DPW
Bradley Beach, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Bradley Beach, Borough of | Continue to implement measures to mitigate ocean and lake flooding due to hurricanes and large storms. This includes the new installation of outfall pipes and bulkheading around Fletcher Lake, bulkheading around Sylvan Lake and continued maintenance of the dunes which run along the entire beachfront. | M | Flooding due to hurricanes, coastal flooding and large storms |  | Mayor, Council, and Fletcher and Sylvan Lake Commission
Bradley Beach, Borough of | Action 14A - Conduct evaluations of emergency facilities to determine the level of protection from flooding and wind damage | M | All |  | Mayor and Council, Office of Emergency Management
Bradley Beach, Borough of | Continue to support and fund the Borough's Community Emergency Response Team | M | All |  | Mayor, Emergency Management Coordinator
Bradley Beach, Borough of | Action 14D - Continue to implement the best management practices for floodplain areas | M | Flooding |  | Mayor, Council, Borough Administrator, Borough Engineer
Brielle, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Brielle, Borough of | Reinforce the First Aid Building to be used as an emergency shelter. Retrofit and make improvements to a dedicated emergency shelter located out of floodprone areas. The improvements would make the shelter resistant to loss of power during hurricanes, nor'easters, and other high wind storms. It would also harden the structure against utility outages due to extreme temperatures. | H | Hurricanes, loss of power, winter storms, nor'easters, heat wave, flooding, storm surge |  | Brielle OEM, Mayor and Council
Brielle, Borough of | Bulkhead restoration on Ocean Avenue to prevent the end of the roadway from collapsing, which would undermine the adjacent properties and can cause flooding during a period of high tide. Any storm that creates a tidal surge would then pose a severe threat to the area and further undermine Ocean Avenue. | M | Flooding, storm surge, hurricanes, nor'easters |  | Brielle OEM, Mayor and Council
Colts Neck, Township of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Colts Neck, Township of | Action 2A - Expand and disseminate GIS and other hazard information on the internet | M | All |  | Township Administration
Colts Neck, Township of | Action 2B - Create mitigation outreach program that helps residents and businesses prepare for disasters | M | All |  | Township Administration
Colts Neck, Township of | Action 11B - Educate residents about driving in winter storms and handling winter related health effects | M | Winter storms and nor'easters |  | Township Administration
Colts Neck, Township of | Action 11C - Promote ice and windstorm resistant trees and trimming to reduce tree related hazards | M | Winter storms and nor'easters |  | Township Administration
Deal, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Deal, Borough of | Set up detention pond and berm system to prevent future flooding for Poplar Brook between Norwood Ave and Ocean Ave | H | Hurricane, tropical storm, nor'easter, winter storm, flood, storm surge, tsunami |  | Business Admin, DPW, OEM, Borough Engineer, Army Corps, State DEP
Deal, Borough of | Widen culverts under roadways in three different streets for Poplar Brook (Norwood Ave, Alymar Ave, Ocean Ave) | H | Hurricane, tropical storm, nor'easter, winter storm, flood, storm surge, tsunami |  | Business Admin, DPW, OEM, Borough Engineer, Army Corps, State DEP, County Bridge Dept, State DOT
Eatontown, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Eatontown, Borough of | Dredge Husky Brook that runs through town, Fix Lewis Street Public Works yard from flooding. | H (#1) | Hurricane and tropical storms, nor'easters, storm surge, flooding |  | Mayor/Council, Borough Engineer
Eatontown, Borough of | Add generators to shelters for emergency power and telecommunications | M (#2) | Hurricane and tropical storms, nor'easters, storm surge, flooding |  | Mayor/Council, Board of Education, Borough Engineer
Eatontown, Borough of | Purchase NOAA Radios and educate residents about storms | M (#3) | Hurricane and tropical storms, nor'easters, storm surge, flooding |  | OEM Coordinator
Englishtown, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Englishtown, Borough of | Conduct routine stream maintenance program and seek financial assistance to clean out stream segments with heavy sediment deposits, Weamaconk Creek and McGellairds Brook | H | Flooding, heavy rain events, nor'easters and hurricanes, spring thaw |  | Mayor, Council
Fair Haven, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Fair Haven, Borough of | Place power transmission lines underground | 1 | Downed power lines during wind or ice storms |  | JCP&L
Fair Haven, Borough of | Replace older damaged utility poles with newer, up-to-date poles | 2 | Downed power lines during wind or ice storms |  | Verizon
Fair Haven, Borough of | Remove or trim trees that would have the potential of falling during a storm | 3 | Threat of injury to the public and damage to property |  | DPW, JCP&L
Farmingdale, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Farmingdale, Borough of | Harden existing shelters for storm resistance | M | All |  | HTOEM
Farmingdale, Borough of | Increase shelter in place capabilities | M | All |  | HTOEM
Farmingdale, Borough of | Purchase, raise or address repetitive flood areas and properties | L | Nor'easter, winter storms, tornado, hurricane |  | HTOEM
Farmingdale, Borough of | Redundant dispatch and EOC upgrade | H | All |  | HTOEM, HTPD
Farmingdale, Borough of | Standby power for emergency needs | H | All |  | HTOEM, HTPD, HTDPW
Farmingdale, Borough of | Backup water purification for shelter and utility outage | H | All |  | HTOEM, HEALTH
Freehold, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Freehold, Borough of | Planning and funding to update communications and backup power systems in the EOC | H | All |  | Mayor, Council and Business Administrator
Freehold, Borough of | Emergency generators installed in our grammar schools that are designated as evacuation centers | H | All |  | Mayor, Council and Local school board
Freehold, Borough of | Create an outreach program to help residents plan for disasters | L | All |  | OEM, Mayor and Council
Freehold, Township of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Freehold, Township of | Action 4E - Conduct routine stream maintenance program to identify areas prone to flooding and seek financial assistance to clean out problem segments | H | Flooding, heavy rain events |  | OEM, Public Works, County, State and Federal agencies
Freehold, Township of | Action 2B - Create mitigation and preparedness outreach program by providing information that helps residents and property owners prepare for disasters | H | All |  | OEM
Freehold, Township of | Action 11B - Educate residents about driving in winter storms and handling winter related health hazards | H | Winter storms and nor'easters |  | OEM
Hazlet, Township of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Hazlet, Township of | 10A - Develop a mapping of wildland/urban interface areas with assistance of the NJFFS | H | Wildfires |  | OEM and Fire Chiefs
Hazlet, Township of | 10B - Put together a list of addresses for route altering during wildfire emergencies that require public warning | H | Wildfires |  | OEM
Hazlet, Township of | 10I - Mitigation for streets, highways, and roads that provide key fire access and fuelbreaks | M | Wildfires |  | Hazlet Public Works
Hazlet, Township of | 10J - With assistance of NJFFS, widen all paths in the wildland area for better access | M | Wildfires |  | OEM, NJFFS
Highlands, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Highlands, Borough of | Action 1E - Update Highlands Flood Mitigation Plan 1999. Use existing flood damage prevention ordinance 0-98-12, flood ID survey results, surface flooding drainage study, and repetitive loss survey results. Include damage surveys and repair cost estimates. | H | Flooding |  | Mayor and Council
Highlands, Borough of | Action 4E - Use flood ID survey results in Highlands Mitigation plan to mitigate damage and losses due to flooding. Specifically undersized drainage pipes, pumping station, and bulkheads. Stormwater runoff from hill sections, tidal conditions and coastal flooding create sever flooding conditions (pumps, storm drain replacement and repair) | H | Flooding due to stormwater runoff, tidal flooding, and coastal floods. Hurricanes and nor'easters |  | Mayor and Council
Highlands, Borough of | Action 7B - Reduce the possibility of damage and losses due to coastal erosion and wave action (bulkheads, repair wharves) | H | Flooding due to inland and coastal floods, hurricanes and nor'easters |  | Mayor and Council
Highlands, Borough of | Action 9D - Reduce the possibility of damage and losses due to landslides. Highlands has specific areas identified (9A) prone to landslides. Damage as a result of a landslide currently has Bayside Drive closed. | H | Landslides due to steep slopes and slump blocks |  | Mayor and Council
Highlands, Borough of | Action 2C - Planning for and funding improvements to telecommunication and electrical systems at critical facilities including facilities used for EOC and as local shelters. | M | All |  | Mayor and Council
Highlands, Borough of | Action 13E - Install hurricane clips and wind shutters on existing development particularly emergency facilities and shelters built before existing codes were adopted to offer some degree of protection | M | Wind events |  | Mayor and Council
Highlands, Borough of | Action 14A - Reduce the possibility of damage to emergency facilities by conducting an evaluation to determine existing level of protection, particularly to flooding and implementing recommendations. | M | All (particularly flooding) |  | Mayor and Council
Holmdel, Township of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Holmdel, Township of | Retrofit existing sewer pump stations with hurricane clips/straps as needed to reduce the possibility of loss of municipal sewer service due to windstorms/hurricanes | H | Wind events |  | Township Administrator
Holmdel, Township of | Require mulch on or adjacent to commercial shopping area parking lots to be fire resistant | H | Fire |  | Township Committee
Howell, Township of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Howell, Township of | Harden existing shelters for storm resistance | M | All |  | HTOEM
Howell, Township of | Increase shelter in place capabilities | M | All |  | HTOEM
Howell, Township of | Purchase, raise or address repetitive flood areas and properties | L | Nor'easter, winter storms, tornado, hurricane |  | HTOEM
Howell, Township of | Redundant dispatch and EOC upgrade | H | All |  | HTOEM, HTPD
Howell, Township of | Standby power for emergency needs | H | All |  | HTOEM, HTPD, HTDPW
Howell, Township of | Backup water purification for shelter and utility outage | H | All |  | HTOEM, HEALTH
Interlaken, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Interlaken, Borough of | Develop mitigation steps to reduce damage and losses due to flooding through control of stormwater runoff and more efficient drainage and discharge to ocean waters | H | nor'easters, hurricanes, flooding caused by inland and coastal floods, storm surge |  | Mayor and Council, Deal Lake Commission
Keansburg, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Keansburg, Borough of | 1A - Enact hazard zoning ordinances | H | Flooding |  | Mayor and Council, Zoning Board, Planning Board, Code Officials
Keansburg, Borough of | 1B - Specifically allow variances on foundations of newly built structures | H | Flooding due to inland and coastal floods, hurricanes, nor'easters, and storm surges |  | Mayor and Council, Zoning Board, Planning Board, Code Officials
Keansburg, Borough of | Develop mitigation steps to reduce damage and losses due to flooding, through the control of water flow and a more efficient drainage | H | Flooding due to inland and coastal floods, hurricanes, nor'easters, and storm surges |  | Mayor and Council, Borough Manager, Water Plan, Borough Engineer, Public Works
Keansburg, Borough of | Create an outreach program to help residents prepare for disasters | H | Flooding due to inland and coastal floods, hurricanes, nor'easters, and storm surges |  | Mayor and Council, Borough Manager, OEM Coordinators
Keansburg, Borough of | Develop a plan and seek funding for backup electric in critical care facilities | H | Flooding due to inland and coastal floods, hurricanes, nor'easters, and storm surges |  | Mayor and Council, Borough Manager, OEM Coordinators
Keansburg, Borough of | Reduce water use for landscaping by imposing mandatory water use restrictions | L | Droughts |  | Mayor and Council, Borough Manager, OEM Coordinators, Water Department, Supervisor of Public Works
Keyport, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Keyport, Borough of | Fireman's Park bulkhead extension from bulkhead elevation 8.1 to Monmouth County bridge on W. Front Street | H | Flooding, wave action |  | Mayor and Council
Keyport, Borough of | Raising of Green Grove Avenue at Chingarora Creek culvert crossing to alleviate storm flooding of this coastal evacuation route | H | Flooding |  | Mayor and Council
Lake Como, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Lake Como, Borough of | Action 1C - Enact hazard zoning/ordinances on height of homes in flood areas to place foundations above floodplain | H | Flooding |  | Mayor and Council
Lake Como, Borough of | Develop mitigation action steps to reduce damage and losses due to flooding caused by inland and coastal floods (hurricanes and nor'easters), which impact Lake Como. This would be achieved by controlling the water flow by a more efficient drainage system into the ocean. Specifically by utilizing pumps at Lake Como to control floodwaters | H | Flooding, hurricanes, and nor'easters |  | Mayor and Council
Little Silver, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Little Silver, Borough of | Action 4E - Develop mitigation steps to reduce damage and losses due to flooding caused by coastal flooding, hurricanes, nor'easters at the end of Little Silver Point Road (Howard's Beach) specifically by new outfall structure for storm drainage system | H | Flooding due to coastal storms, hurricanes, nor'easters and storm surge |  | Mayor and Council
Little Silver, Borough of | Action 4F - Reduce the possibility of flood damage by conducting a stream maintenance plan | M | Flooding due to heavy rain events, hurricanes, nor'easters, and storm surge |  | Mayor and Council
Loch Arbour, Village of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Loch Arbour, Village of | Action 4E - Develop mitigation steps to reduce damage and losses caused by inland and coastal floods, hurricanes and nor'easters at Deal Lake through control of water flow and more efficient drainage to the Atlantic Ocean by electrification of Deal Lake flume gates. Note: The Village is a member of the NFIP and has implemented a local warning system. | H | Flooding due to inland and coastal floods, hurricanes and nor'easters |  | Deal Lake Commission, DEP, area municipal governing bodies
Loch Arbour, Village of | Action 4F - Reduce the possibility of flood damage by conducting stream maintenance and clearing sediment from Deal Lake and surrounding streams in the watershed | H | Flooding due to inland and coastal floods, hurricanes and nor'easters |  | Deal Lake Commission, DEP, area municipal governing bodies, county and state
Loch Arbour, Village of | Action 4H - Reduce the possibility of flooding at the eastern terminus of Deal Lake by implementing stormwater retention projects identified by the Deal Lake Commission in the Regional Stormwater Management Plan for the Deal Lake Watershed | H | Flooding due to inland and coastal floods, hurricanes and nor'easters |  | See above
Long Branch, City of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Long Branch, City of | Enact updated hazard zoning/ordinances. Specifically to conform to FEMA's new FIRM program | H | Flooding |  | Mayor and Council
Long Branch, City of | Develop mitigation steps to reduce damage and losses due to flooding caused by inland and coastal floods, hurricanes and nor'easters. Through control of water flow and through more efficient drainage to ocean and river. Specifically, install drainage and storm water pipe to control flood waters and increase strategic locations to control flow. | H | Flooding due to inland and coastal floods, hurricanes and nor'easters |  | Mayor and Council
Long Branch, City of | Develop mitigation steps to reduce damage and losses due to flooding caused by excessive precipitation in areas surrounding City Hall from Broadway to Morris Avenue | H | Flooding due to excessive precipitation and improper pipe sizing for increased development |  | Mayor and Council
Long Branch, City of | Reduce the likelihood of flood damage by creating and executing a stream and lake maintenance plan | M | Inland and coastal flooding |  | State DEP, Mayor and Council
Long Branch, City of | Develop and implement a mitigation plan to control flash flooding condition under NJ Transit Railroad trestle near train station | M | Poor elevation and complicated by poor drainage and improper pitch of roadways |  | Mayor and Council
Manalapan, Township of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Manalapan, Township of | Action 1 - Holiday Lake dredging project. Temporary dewatering and removal of sediment, stream bank stabilization. Construction of an outlet control structure (sluice gate) between gate and existing headwall | H | Flooding, nor'easters, and hurricanes |  | Township Committee, Municipal Engineers
Manasquan, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Manasquan, Borough of | Increase Public Warning Capabilities: Upgrade existing AM Radio station, increase warning siren coverage, implement Reverse911 system, install electronic sign system | H | All |  | Office of Emergency Management with approval from governing body
Manasquan, Borough of | Develop Residential Mitigation Strategies: Develop specific hazard mitigation actions that home/business owners can undertake that will reduce property damage resulting from coastal storms | H | Flooding, wind and lightning |  | Office of Emergency Management with approval from governing body
Manasquan, Borough of | Develop Public Outreach Program: Implement a public outreach program that includes hazards identification, public warning systems and mitigation activities that home/business owners can undertake | H | All |  | Office of Emergency Management
Manasquan, Borough of | Develop digital GIS flood inundation mapping: Develop inundation mapping based upon aerial topographic mapping and incorporating the latest SLOSH values form the US Army Corps | H | Flooding |  | Office of Emergency Management with approval from governing body
Marlboro, Township of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Marlboro, Township of | Action 2D - Establish a stream cleaning program for Deep Run and its tributaries into Old Bridge Township to its deposit into the New Jersey American Water facility in Old Bridge Township | H | Flooding |  | Engineering
Marlboro, Township of | Action 2D - Establish a stream cleaning program for the Yellow Brook and its tributaries up to Buck's Pond in Colts Neck Township | H | Flooding |  | Engineering
Marlboro, Township of | Action 2D - Establish a stream cleaning program for the Barclay Brook and its tributaries through Old Bridge Township to its deposit in the Matchaponix Brook | H | Flooding |  | Engineering
Marlboro, Township of | Action 2D - Establish a stream cleaning program for Melvins Brook and its tributaries through Manalapan Township to its deposit in McGallairds Brook | H | Flooding |  | Engineering
Marlboro, Township of | Action 4A - Increase public awareness relating to the risks associated with severe weather events and the importance of personal preparedness | H | All |  | Administration
Marlboro, Township of | Action 1D - Improve the Township's ability to alert and warn the public in the event of impending severe events | H | All |  | Office of Emergency Management
Matawan, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Matawan, Borough of | Replacement of the Lake Lefferts Dam | L | Flooding due to inland flooding, hurricanes and nor'easters |  | Mayor/Council, Monmouth County Engineering Dept.
Matawan, Borough of | Replacement of the Lake Matawan Dam | L | Flooding due to inland flooding, hurricanes and nor'easters |  | Mayor/Council, Monmouth County Engineering Dept.
Matawan, Borough of | Reduce flooding frequency of Aberdeen Road - downstream from Lake Lefferts - elevate roadway | M | Flooding due to inland flooding, hurricanes and nor'easters |  | Mayor/Council, Borough Engineer
Middletown, Township of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Middletown, Township of | Action 1C Enact Hazard Zoning/Ordinances. Township recently amended ordinance for height flexibility. Height can be measured after the lot is filled to place foundations above floodplain. Note: Township is a member of NFIP (1A) and has a Stormwater Management Plan (1E) | M | 100yr flood |  | Planning and Building Department
Middletown, Township of | Within the flood hazard areas, raise dwelling units one foot above base flood elevation | H | 100yr flood |  | State DEP and Planning Department
Middletown, Township of | Action 4F - Conduct a routine stream and ditch maintenance program in floodprone areas | M | mosquito control |  | In conjunction with Monmouth County Mosquito Control Commission - Regular program of stream and ditch maintenance
Middletown, Township of | Wetlands maintenance and removal of invasive plant species | H | flooding and fire hazards |  | Mayor and Township Committee
Middletown, Township of | Maintenance and upgrade of stormwater management structures and facilities | H | flood and mosquito control |  | Mayor and Township Committee
Millstone, Township of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Millstone, Township of | Develop mitigation steps to reduce damage and losses due to flooding through control of stormwater runoff and more efficient drainage and discharge to five major streams | H | Severe thunderstorms, hurricanes, nor'easters, storm surge |  | Mayor and Township Committee and OEM Coordinator
Millstone, Township of | Develop mitigation steps to reduce significant damage from losses due to wildfires | H | Wildfires, thunderstorms, fallen electrical wires, plane crashes and motor vehicle accidents |  | Mayor and Township Committee and OEM Coordinator
Monmouth Beach, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Monmouth Beach, Borough of | Install drainage to relieve flooding from flood prone areas. Example: Johnson St./Anderson St./Drew Ct./Valentine St. | H | High tide flooding, northeast storms, flash flooding due to heavy rains, hurricane, snow event |  | Local government
Neptune, Township of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Neptune, Township of | Identify outfalls to Category One waterways and other receiving bodies, retrofit with Tideflex or equivalent and install stormceptors prior to discharge to waterbody | H | Flooding, environmental, wind, storm |  | Township Committee, Engineering
Neptune, Township of | Seek funding for dredging of Shark River. Coordination with adjoining municipalities | H | Flooding, environmental, storm |  | Township Committee, Engineering
Neptune, Township of | Seek funding for replacement of bulkhead along Shark River | H | Flooding, storm, environmental |  | Township Committee, Engineering, Public Works
Neptune, Township of | Implement GIS based hazard data on the Neptune website and through publications made available to the public | H | Flooding, wind, storm |  | Township Committee, Building, Construction
Neptune, Township of | Encourage public to build/modify to be more disaster resistant building. Further educate construction department to aid public in same | H | Flooding, storm, wind, hurricane |  | Township Committee, Building, Construction, Zoning
Neptune, Township of | Include in Neptune Day a public awareness information booth. Preparation of informational packets for safety, mitigation, evacuation routes and available resources | H | Flood, wind, storm |  | Building, Construction
Neptune, Township of | Preparation of study of streams and capacity and prioritize. Preparation and analysis of access and plan to desnag/desilt streams and waterways | M | Flooding, storm, environmental |  | Township Committee, Engineering
Neptune, Township of | Seek funding for bank stabilization along Shark River. Prepare plan and specifications for Bank Stabilization location, extents and cross-section | M | Flooding, storm |  | Township Committee
Neptune, Township of | Seek funding for lake dredging, preparation of plans and specifications for dredging of Lake Fletcher/Wesley/Alberta | M | Flooding, storm, environmental |  | Township Committee, Environmental
Neptune, Township of | Preparation of plans and specifications for construction of salt dome | M | Storm, environmental |  | Township Committee, Engineering
Neptune, Township of | Preparation of hazard overlay zones | L | Storm, flooding |  | Township Committee
Neptune, Township of | Study to determine extent of beach replenishment at Ocean Grove. Preparation of plans and specifications for same | L | Flooding, storm |  | Township Committee, Engineering
Neptune City, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Neptune City, Borough of | Action 2C - Implement a public awareness campaign on the use of grounded electric outlets and surge protectors | H | Lightning strikes |  | Office of Emergency Management
Neptune City, Borough of | Action 11B - Implement a public awareness campaign on driving in winter storms and handling related health effects | H | Winter storms and nor'easters |  | Office of Emergency Management
Neptune City, Borough of | Action 2C - Develop a plan and seek funding for backup electric for shelters | M | All |  | Mayor and Council
Ocean, Township of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Ocean, Township of | Set up detention pond and berm system to prevent future flooding for Poplar Brook | H | Hurricane, tropical storm, nor'easter, winter storm, flood, storm surge, tsunami |  | Twp Manager, DPW, OEM, Twp Engineer, Army Corps, State DEP
Ocean, Township of | Widen culverts under roadways in three different streets for Poplar Brook | H | Hurricane, tropical storm, nor'easter, winter storm, flood, storm surge, tsunami |  | Twp manager, DPW, OEM, Twp Engineer, Army Corps, State DEP, County Bridge Dept, State DOT
Ocean, Township of | Build a detention pond to gather more water and prevent large amounts of water to move downstream in Whalepond Brook | H | Hurricane, tropical storm, nor'easter, winter storm, flood, storm surge, tsunami |  | Twp Manager, DPW, OEM, Twp Engineer, Army Corps, State DEP
Ocean, Township of | Widen culverts under roadways in three different streets for Poplar Brook | H | Hurricane, tropical storm, nor'easter, winter storm, flood, storm surge, tsunami |  | Twp manager, DPW, OEM, Twp Engineer, Army Corps, State DEP, County Bridge Dept, State DOT
Ocean, Township of | Planning and funding improvements to telecom and electrical systems at critical facilities including facilities used for EOC and as local shelters | M | Hurricane, tropical storm, nor'easter, winter storm, flood, storm surge, tsunami, hail storm, wildfire |  | Twp Manager, DPW, OEM
Oceanport, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Oceanport, Borough of | Infrastructure-critical facility - relocation of borough hall and DPW. Phase 1 -acquire property for relocation | H - Priority 1 | Hurricane and tropical storms, nor'easter, storm surge, flood |  | Mayor/Council, Borough Engineer
Oceanport, Borough of | Infrastructure-critical facility - relocation of borough hall and DPW. Phase 2 - Construction of New Facility | H - Priority 1 | Hurricane and tropical storms, nor'easter, storm surge, flood |  | Mayor/Council, Borough Engineer
Oceanport, Borough of | Remediation of Turtle Mill Floodway - stream cleaning | M - Priority 2 | Hurricane and tropical storms, nor'easter, storm surge, flood |  | Borough Engineer
Oceanport, Borough of | Infrastructure - examination of storm water system, Port-au-Peck section; Phase 1 | M - Priority 3 | Hurricane and tropical storms, nor'easter, storm surge, flood |  | Borough Engineer
Oceanport, Borough of | Infrastructure - examination of storm water system, Port-au-Peck section; Phase 2 | M - Priority 3 | Hurricane and tropical storms, nor'easter, storm surge, flood |  | Borough Engineer
Oceanport, Borough of | Infrastructure - Remediation Roadway Flooding - Grading, Elevating, or backflow preventers | L - Priority 4 | Hurricane and tropical storms, nor'easter, storm surge, flood |  | Borough Engineer
Red Bank, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Red Bank, Borough of | Enact hazard zoning/ordinances. Specifically, allow variances on height of homes in flood areas to place foundations above floodplain | H | Flooding |  | Mayor and Council
Red Bank, Borough of | Develop plans for a community emergency alerting system | H | All |  | Mayor and Council, Police/Fire/OEM
Red Bank, Borough of | Develop plans and mitigation steps to reduce or eliminate flood and erosion to Marine Park | H | Flooding due to coastal floods, hurricanes and nor'easters |  | Mayor and Council
Red Bank, Borough of | Reduce the possibility of flood damage by conducting a storm management maintenance plan and cleaning and maintaining the existing system | M | All |  | Mayor and Council
Red Bank, Borough of | Planning for and funding improvement to infrastructure system of the borough water and sewer system | M | All |  | Mayor and Council
Red Bank, Borough of | Reduce the possibility of damage to emergency facilities by conducting an evaluation to determine existing level of protection and implementing recommendations | M | All |  | Mayor and Council
Roosevelt, Borough of | Did not participate in the 2009 Plan
Rumson, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Rumson, Borough of | Implement early flood warning system for Shrewsbury and Navesink Rivers as a shared service with other towns along the rivers | M - #1 | Flooding, nor'easter, hurricane, storm surge |  | Mayors and Council members of all river towns; Monmouth University; Stephens Institute of Technology
Rumson, Borough of | Enact new FEMA flood maps as part of planning and zoning regulations | M - #2 | Flooding, nor'easter, hurricane, storm surge |  | Mayor and Council, Planning Board, Zoning Board
Rumson, Borough of | Implement stream and pond cleaning to speed drainage of flood prone areas and follow up with regular maintenance | M - #3 | Flooding, heavy rain, nor'easter, hurricane, storm surge |  | Mayor and Council, Public Works, Monmouth County Mosquito Commission
Rumson, Borough of | Upgrade shelter facility located at Rumson Fair Haven Regional High School, including emergency power facility | H - #4 | Flooding, nor'easter, hurricane, extreme heat, storm surge, winter storm |  | Mayor and Council, Board of Education, OEM
Rumson, Borough of | Continue to maintain current warning systems that are already operational including website. AM radio, Reverse911 calling system and emergency siren alerting system. | H - #5 | Nor'easter, hurricane, flooding, storm surge, extreme heat, winter storm |  | Mayor and Council, OEM Director, Police
Rumson, Borough of | Tree maintenance of shade trees along streets in community; increase effectiveness of Public Works to clear trees in event of storm | M/H - #6 | Wind and rain events, winter storms |  | Mayor and Council, OEM Director, Public Works
Sea Bright, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Sea Bright, Borough of | Develop a storm, flood and wind action plan which will include police, fire, and public works volunteer groups to allow Sea Bright to be methodically protected during a storm or flood event | H | Flood, wind, storm |  | Mayor & Council, Emergency Management
Sea Bright, Borough of | Explore and implement a project to elevate private homes in floodprone areas with state or federal funds | H | Flood, storm |  | Construction Office
Sea Bright, Borough of | Support and create a hazardous material response team including training and equipment to protect by the citizens of Sea Bright and the environment, rather than relying on state, federal or county agencies | H | Storm, environmental |  | Emergency Management
Sea Bright, Borough of | Develop a town wide strategy to aid both local, county, state and federal officials to provide the replacement of sand along the Atlantic Ocean Beach for protection of both the NJSH Route 36 corridor, local residences, businesses and bulkheads | H | Storm, environmental |  | Mayor and Council
Sea Bright, Borough of | Develop a town wide strategy to aid both local, county, state and federal officials to provide the reconstruction of bulkheads along the Shrewsbury River for protection of both the NJSH Route 36 corridor, local residences, businesses and bulkheads | H | Storm, environmental |  | Mayor and Council
Sea Bright, Borough of | Encourage citizens and businesses when rebuilding or modifying their buildings to provide underground utilities in order to promote utilities that are generally not prone to damage during high winds and flooding incidents | M | Flood, wind, storm |  | Mayor and Council, Building Department
Sea Bright, Borough of | Include in Sea Bright Day a public education and awareness component for hazard mitigation, citizen safety, include mitigation techniques highlighting our available resources | M | Flood, wind, storm |  | Mayor and Council, Clerk
Sea Bright, Borough of | Provide additional support and training for the Building Department on wind and flood resistant structures, including information on hurricane clips, wind shutters, beyond the minimum building code | M | Wind, flood |  | Building Department
Sea Girt, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Sea Girt, Borough of | Enact hazard zoning/ordinances. Specifically allow variances on height of homes in flood areas to place foundations above floodplain | H | Flooding |  | Mayor and Council
Sea Girt, Borough of | Develop mitigation steps to reduce damage and losses due to flooding caused by inland and coastal floods, hurricanes and nor'easters at local ponds (Wreck Pond) through control of water flow and through more efficient drainage to ocean. Specifically, pumps at Wreck Pond to control floodwaters and use of weirs in strategic locations to control flow (all done in conjunction with Spring Lake). | H | Flooding due to inland and coastal floods, hurricanes and nor'easters |  | Mayor and Council
Sea Girt, Borough of | Reduce the possibility of flooding at Wreck Pond by implementing stormwater retention projects identified by the Wreck Pond Regional Stormwater Management Committee in Subregion 12 watershed | H | Flooding due to inland and coastal floods, hurricanes, and nor'easters |  | Mayor and Council
Sea Girt, Borough of | Reduce the possibility of flood damage by conducting a Stream Maintenance Plan and cleaning out sediment at Wreck Pond and Black Creek - will need to work with Spring Lake, Spring Lake Heights, and Wall on this. | M | Inland and coastal flooding (has additional impact on health and beach environment) |  | State DEP, Mayor and Council
Sea Girt, Borough of | Planning for and funding improvements to communications and electrical systems at critical facilities including facilities used for EOC and as local shelters | M | All |  | Mayor and Council
Sea Girt, Borough of | Reduce the possibility of damage to emergency facilities by conducting an evaluation to determine existing level of protection, particularly to flooding, and implementing recommendations | M | All |  | Mayor and Council
Shrewsbury, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Shrewsbury, Borough of | Upgrade stormwater infrastructure on Haddon Ave | H | Flooding |  | Borough Engineer
Shrewsbury, Borough of | Upgrade stormwater infrastructure on Monroe Ave | H | Flooding |  | Borough Engineer, Monmouth County, NJDEP oversight
Shrewsbury, Borough of | Upgrade stormwater infrastructure on Trafalgar Pl | H | Flooding |  | Borough Engineer
Shrewsbury, Borough of | Stream Management | H | Flooding |  | Borough Engineer/DPW, NJDEP permits required
Shrewsbury, Borough of | Upgrade stormwater infrastructure on Newman Springs Road | H | Flooding |  | County and Borough Engineer
Shrewsbury, Borough of | CERT programs and public outreach, including potable water conservation and drought limitations | M | Various |  | OEM
Shrewsbury, Township of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Shrewsbury, Township of | Action 2C - Planning for funding and improvements to telecomm and electrical systems at critical facilities including EOC and local shelters | M | All |  | Mayor and Council
Shrewsbury, Township of | Action 1E - Develop stormwater management plan | M | Health and environment |  | Mayor and Council
Spring Lake, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Spring Lake, Borough of | Action 1C - Enact hazard zoning/ordinances. Specifically allow variances on height of homes in flood areas to place foundations above floodplain. | H | Flooding |  | Mayor and Council
Spring Lake, Borough of | Action 4E - Develop mitigation steps to reduce damage and losses due to flooding caused by inland and coastal floods, hurricanes and nor'easters at local ponds (Wreck Pond and Lake Como) through control of water flow and through more efficient drainage to ocean. Specifically, pumps at Wreck Pond and/or Lake Como to control floodwaters and sue of weirs in strategic locations to control flow. | H | Flooding due to inland and coastal floods, hurricanes, and nor'easters |  | Mayor and Council
Spring Lake, Borough of | Action 4F - Reduce the possibility of flood damage by conducting a stream maintenance plan and cleaning out sediment at Wreck Pond and Black Creek | M | Inland and coastal flooding. (has additional impact on health and beach environment) |  | State DEP, Mayor and Council
Spring Lake, Borough of | Action 4H - Reduce the possibility of flooding and increase early warning of potential flood conditions at Wreck Pond by implementing stormwater retention projects identified by the Wreck Pond Brook Regional Stormwater Management Plan (RSWMP) committee in Subregion 12 watershed and by implementing sensor systems (preferably USGS) in the watershed | H (highest priority) | Flooding (due to inland and coastal floods, hurricanes, and nor'easters) |  | Mayor and Council
Spring Lake, Borough of | Action 2C - Planning for funding and improvements to telecomm and electrical systems at critical facilities including EOC and local shelters | M | All |  | Mayor and Council
Spring Lake, Borough of | Action 14A - Reduce the possibility of damage to emergency facilities by conducting an evaluation to determine existing level of protection, particularly to flooding, and implementing recommendations | M | All |  | Mayor and Council
Spring Lake Heights, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Spring Lake Heights, Borough of | Action 1C - Explore the need for hazard zoning and high risk hazard land use ordinances, raising utilities, exceeding height requirements | H | Flooding, nor'easters, hurricanes, storm surge, heavy rain events |  | Mayor and Council
Spring Lake Heights, Borough of | Action 4D - Continue to implement the best mitigation practices for floodplain areas | H | Flooding, nor'easters, hurricanes, storm surge, heavy rain events |  | Mayor and Council
Spring Lake Heights, Borough of | Action 2B - Create a mitigation outreach program to prepare residents for disaster | H | Flooding, nor'easters, hurricanes, storm surge, heavy rain, drought, extreme heat, winter storm |  | Mayor and Council
Tinton Falls, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Tinton Falls, Borough of | Action 1E - Develop a stormwater management plan that includes subdivision regulations to control runoff; both for flood reduction and to minimize saturated soils on steep slopes that can cause landslides. (Sycamore Avenue storm drainage; Water Street erosion (Pine Brook)) | H | Promote disaster resistant development |  | Mayor and Council
Tinton Falls, Borough of | Action 11C - Ice and windstorm resistant trees and landscaping practices to reduce related hazards (throughout municipality) | H | Winter storms |  | Mayor and Council
Tinton Falls, Borough of | Action 9B - Locally identify and map specific areas of potential slope failure and limit future development in these areas (Water Street into Pine Brook) | H | Landslides |  | Mayor and Council
Tinton Falls, Borough of | Action 4F - Conduct a routine maintenance program and seek financial assistance to clean out stream segments with heavy sediment deposits (Whale Pond Brook, Jumping Brook) | H | Flooding by hurricanes, severe storm, nor'easters |  | Mayor and Council
Tinton Falls, Borough of | Action 4G - Develop specific mitigation solutions for floodprone roadways and intersections under the leadership of NJDOT. Develop a work plan for when sites will be surveyed and what role the Borough can play in selection and implementation of mitigation activities (County Highway 13A, County Highway 16, Hope Road) | H | Flooding by hurricanes, severe storm, nor'easters |  | Mayor and Council
Tinton Falls, Borough of | Action 4H - Implement identified stormwater recharge, rate or volume projects identified in Regional Stormwater Management Plans to decrease 'flash' in streams during/after storm events | H | Flooding by hurricanes, severe storm, nor'easters |  | Mayor and Council
Tinton Falls, Borough of | Action 9D - Consider adopting a steep slope ordinance, if one is not already in place, to regulate development on these higher risk areas (Water Street, Jumping Brook) | H | Landslides |  | Mayor and Council
Tinton Falls, Borough of | Action 2B - Create a mitigation outreach program to prepare residents for disasters. Build and support local capacity to enable the public to prepare for, respond to, and recover from disasters. | M | All |  | Mayor and Council
Tinton Falls, Borough of | Action 2E - Support and fund Community Response Team (CERT) programs that also include a mitigation component. Build and support local capacity to enable the public to prepare for, respond to, and recover from disasters (note: borough has existing CERT program) | M | All |  | Mayor and Council
Tinton Falls, Borough of | Action 10A - In consultation with NJFFS, local fire service, develop mapping of wildland/urban interface areas | M | Wildfires |  | Mayor and Council, NJFFS
Tinton Falls, Borough of | Action 10C - In consultation with NJFFS, local fire service, review local EOPs for possible wildfire components regarding fire rescue, alert warning, and communications | M | Wildfires |  | Mayor and Council, NJFFS
Tinton Falls, Borough of | Action 10E - Initiate a public outreach program for homeowners to reduce the possibility of damage and losses due to wildfires | M | Wildfires |  | Mayor and Council, NJFFS
Tinton Falls, Borough of | Action 10I - Mitigation for streets. Highways and roads that provide key fire access and fuel breaks | M | Wildfires |  | Mayor and Council, NJFFS
Tinton Falls, Borough of | Action 11A - Promote (or purchase, for critical facilities) NOAA weather radios | L | Winter storms |  | Mayor and Council
Tinton Falls, Borough of | Action 11B - Educate residents about driving in winter storms and handling winter-related health effects | L | Winter storms |  | Mayor and Council
Union Beach, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Union Beach, Borough of | Raise the roadway elevation of the floodprone section of Florence Avenue | 1 | Flooding |  | Borough Engineer
Union Beach, Borough of | Raise the roadway elevation of the floodprone section of Jersey Avenue | 2 | Flooding |  | Borough Engineer
Union Beach, Borough of | Raise the roadway elevation of the floodprone intersection of Spruce Street and Center Street | 3 | Flooding |  | Borough Engineer
Union Beach, Borough of | Relocation of Harris Garden Fire Company Building to a site outside of the floodprone area | 4 | Flooding |  | Mayor and Borough Council, Office of Emergency Management, Fire Department
Union Beach, Borough of | Raise the elevation of the floodprone Scholer Park parking lot | 5 | Flooding |  | Borough Engineer
Union Beach, Borough of | Maintenance of the existing shore protection features (bulkhead, beach area) | 6 | Coastal erosion and wave action |  | Borough Engineer, Public Works
Union Beach, Borough of | Cleaning and maintenance of the existing storm drains and inlets | 7 | Flooding |  | Public Works
Union Beach, Borough of | Cleaning and maintenance of receiving waterways and creeks | 8 | Flooding |  | Public Works, County Mosquito Commission
Union Beach, Borough of | Installation of flood warning signs in floodprone areas | 9 | Flooding |  | Office of Emergency Management
Union Beach, Borough of | Upgrade Borough's existing warning system | 10 | Flooding, coastal erosion, and wave action |  | Office of Emergency Management, Police Department
Union Beach, Borough of | Upgrade emergency generator at police headquarters | 11 | Flooding, coastal erosion, and wave action |  | Office of Emergency Management, Police Department
Union Beach, Borough of | Implementation of the Army Corps of Engineers Shore Protection and Flood Control Project | 12 | Flooding, coastal erosion, and wave action |  | Mayor and Borough Council, ACOE, NJDEP
Upper Freehold, Township of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Upper Freehold, Township of | Action 4D - Ellisdale Road - Installation of sheet piling, increase culvert size, construct ditching and reconstruction of 700 LF of roadway at Bridge U-52 | H (#1) | Flooding due to inland flooding, hurricanes and nor'easters |  | Township Committee
Upper Freehold, Township of | Action 4F - Cleaning of sediment and debris and removal of fallen trees which block waterways. Examples are at Bridges U-15 Breza Road and U-52 Ellisdale Road | H (#2) | Flooding due to fallen trees caused by storm drainage |  | Township Committee
Upper Freehold, Township of | Action 4D - Roadway bank protection at Bridge U-34 Sharon Station Road; Bridge U-53 Provinceline Road; and Bridges U-47 & U-48 Walnsmill Road | H (#3) | Roadway erosion caused by flooding |  | Township Committee
Wall, Township of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Wall, Township of | Action 10A - In conjunction with NJFFS and local Forest Fire Warden, develop mapping of wildland/urban interface areas | M | Wildfires |  | Township Committee
Wall, Township of | Action 2B - Create a mitigation outreach program. Specifically, by using a website and media outreach to assist residents prepare for disasters | M | All |  | Township Committee
Wall, Township of | Action 10B - Develop inventory of addresses for route alerting during wildfire emergencies that require public warning and information. Specifically by implementing reverse telephone notification system | H | Wildfire + All |  | Office of Emergency Management, Police Department
Wall, Township of | Action 3B - Develop and adopt an emergency water allocation strategy to be implemented during severe drought | H | Drought |  | Township Committee
Wall, Township of | Action 4H - Reduce the possibility of flooding at Wreck Pond by implementing stormwater retention projects identified by the Wreck Pond Regional Stormwater Management Committee in Subregion 12 watershed | H | Flooding due to inland and coastal floods, hurricanes, and nor'easters |  | Township Committee and Township Engineer
West Long Branch, Borough of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
West Long Branch, Borough of | Drainage remediation project servicing West Long Branch, Long Branch, Monmouth County property, and Monmouth University property | H (#1) | Hurricane, tropical storm, nor'easter, flood |  | Borough Engineer
West Long Branch, Borough of | Remediation of Turtle Mill Floodway - stream cleaning | M (#2) | Hurricane, tropical storm, nor'easter, flood |  | Borough Engineer